## assignedtasks
assigned_id | assignedto | project_id | task_id | task_name | task_deadline | assigned_date | assigned_time
1 | 3 | 1 | 1 | Initial inspection of old HVAC units | 2025-10-25 | 2025-10-20 | 8:00
2 | 4 | 1 | 2 | Clear out dust and debris from main ceiling vents | 2025-11-02 | 2025-10-26 | 8:00
3 | 5 | 1 | 3 | Mount and wire new carrier units on the roof | 2025-11-12 | 2025-11-03 | 8:00
4 | 3 | 1 | 4 | Run system diagnostics and airflow tests | 2025-11-15 | 2025-11-13 | 8:00
5 | 4 | 2 | 5 | Jackhammer and remove old ceramic lobby tiles | 2025-11-22 | 2025-11-15 | 8:00
6 | 5 | 2 | 6 | Level the concrete subfloor and apply moisture barrier | 2025-11-30 | 2025-11-23 | 8:00
7 | 3 | 2 | 7 | Cut and install new marble floor tiles | 2025-12-14 | 2025-12-01 | 8:00
8 | 4 | 2 | 8 | Apply grout, seal the floor, and run the floor polisher | 2025-12-20 | 2025-12-15 | 8:00
9 | 5 | 3 | 9 | Identify and tag all dead CAT6 cables under the raised floor | 2026-01-12 | 2026-01-05 | 8:00
10 | 3 | 3 | 10 | Pull out old wiring and install new cable trays | 2026-01-25 | 2026-01-13 | 8:00
11 | 4 | 3 | 11 | Install secondary precision air conditioning (PAC) unit | 2026-02-08 | 2026-01-26 | 8:00
12 | 5 | 3 | 12 | Monitor server temps during peak load with new AC running | 2026-02-13 | 2026-02-09 | 8:00
13 | 3 | 3 | 13 | Ttest | 2026-04-07 | 2026-04-05 | 23:01