## task_comments
commentID | project_ID | task_ID | user_ID | commentText | created_at
1 | 1 | 1 | 3 | Started the roof inspection. The old unit casing is completely rusted out. | 2025-10-21 09:15
2 | 1 | 1 | 2 | Copy that Bob. Make sure to photograph the serial numbers before removal so I can update the asset registry. | 2025-10-21 09:45
3 | 1 | 1 | 3 | Done. Uploaded the photos to the shared drive. Task completed. | 2025-10-24 14:25
4 | 1 | 2 | 4 | Duct cleaning is taking a bit longer than expected. Found a massive buildup in the east wing. | 2025-10-28 11:00
5 | 1 | 2 | 5 | I can bring the heavy-duty HEPA vacuum from the basement storage if you need it, Charlie? | 2025-10-28 11:15
6 | 1 | 2 | 4 | That would be a lifesaver, Diana. Thanks! I am up on the ladder near room 302. | 2025-10-28 11:20
7 | 1 | 4 | 3 | Airflow tests are passing with flying colors. We are getting a 40% increase in circulation. | 2025-11-14 09:30
8 | 2 | 5 | 4 | Demolition started. It is incredibly loud out here, we might need to put up sound barriers for the front desk staff. | 2025-11-16 10:00
9 | 2 | 5 | 2 | Good call, Charlie. I will have building management set up temporary acoustic panels tonight. | 2025-11-16 10:30
10 | 2 | 7 | 3 | Heads up: three boxes of the marble tiles arrived cracked. I am sorting out the good ones now. | 2025-12-05 13:10
11 | 2 | 7 | 2 | Ugh, typical supplier issue. Use what you can, I will process an RMA for the broken boxes. | 2025-12-05 13:25
12 | 2 | 8 | 4 | Grout is setting nicely. We should keep the lobby roped off until at least tomorrow morning so the sealant cures. | 2025-12-19 09:50
13 | 3 | 9 | 5 | Half of these cables aren't even labeled. This audit is going to be tedious. | 2026-01-06 14:00
14 | 3 | 9 | 3 | Tell me about it. Just use the tone generator, I left it on the IT desk. | 2026-01-06 14:15
15 | 3 | 11 | 4 | PAC unit is mounted. Waiting on the electricians to finish wiring the dedicated breaker before I can turn it on. | 2026-02-05 15:30
16 | 3 | 12 | 5 | Stress test running. Server load is at 85% and the room temp is holding steady at a frosty 18Â°C (64Â°F). Everything looks solid. | 2026-02-13 11:50
17 | 3 | 12 | 2 | Excellent work everyone. Closing out the project now. | 2026-02-13 12:10