## tasks
ID | projectID | label | progress | task_description | assign_status | task_deadline | completion_status | completion_date | completion_time
1 | 1 | Inspection | 100 | Initial inspection of old HVAC units | assigned | 2025-10-25 | completed | 2025-10-24 | 14:30
2 | 1 | Duct Cleaning | 100 | Clear out dust and debris from main ceiling vents | assigned | 2025-11-02 | completed | 2025-11-01 | 16:00
3 | 1 | Unit Install | 100 | Mount and wire new carrier units on the roof | assigned | 2025-11-12 | completed | 2025-11-11 | 11:15
4 | 1 | Final Testing | 100 | Run system diagnostics and airflow tests | assigned | 2025-11-15 | completed | 2025-11-14 | 9:45
5 | 2 | Demolition | 100 | Jackhammer and remove old ceramic lobby tiles | assigned | 2025-11-22 | completed | 2025-11-21 | 17:00
6 | 2 | Subfloor Prep | 100 | Level the concrete subfloor and apply moisture barrier | assigned | 2025-11-30 | completed | 2025-11-29 | 13:20
7 | 2 | Tile Laying | 100 | Cut and install new marble floor tiles | assigned | 2025-12-14 | completed | 2025-12-13 | 15:45
8 | 2 | Grout & Polish | 100 | Apply grout, seal the floor, and run the floor polisher | assigned | 2025-12-20 | completed | 2025-12-19 | 10:00
9 | 3 | Cable Audit | 100 | Identify and tag all dead CAT6 cables under the raised floor | assigned | 2026-01-12 | completed | 2026-01-11 | 11:30
10 | 3 | Wire Removal | 100 | Pull out old wiring and install new cable trays | assigned | 2026-01-25 | completed | 2026-01-24 | 16:10
11 | 3 | Cooling Install | 100 | Install secondary precision air conditioning (PAC) unit | assigned | 2026-02-08 | completed | 2026-02-07 | 14:00
12 | 3 | Stress Test | 100 | Monitor server temps during peak load with new AC running | assigned | 2026-02-13 | completed | 2026-02-13 | 12:00
13 | 3 | Ttest | 100 | Sjshje | assigned | 2026-04-07 | completed | 2026-04-05 | 23:03